## Acronyms
User
Acronyms | Description
Mbe.off | Membership officer
Fd.Stf | Front-desk Staff
Tel.Stf | Telephone Staff
Acc | Accountant
Salesman | Sales with Tablet
Mbe | Member (anywhere)
HKGTA | All staff in HKGTA
Mkt.off | Marketing Office
RR | Restaurant/Retail Staff
Legend
Acronyms | Description
BV | Business Value
SP | Story Point
Pri | Priority

## Admission Structure
Admission Rights structure (a sample)
Pass Type(The Academy Card)
Admission Type | Full | Weekday | Day | Temp |  |  | FP | FD | WP | WD | DH | DG | TV | TC
Primary Member | FP | WP |  |  | in-scope facilities | Golfing bay | l |  | l |  |  | ¢
Dependent Member | FD | WD |  |  |  | Tennis Court | l |  | l |  |  | ¢
House member |  |  | DH |  |  | Pro Shop | l |  | l |  |  | ¢ | ¢
Guest member |  |  | DG |  |  | All-Day Dinning | l |  | l |  |  | ¢ | ¢
Contractor |  |  |  | TC |  | Refreshment counters | l |  | l |  |  | ¢ | ¢
[6 empty] | Chinese Restaurant | l |  | l |  |  | ¢ | ¢
[6 empty] | Bar | l |  | l |  |  | ¢ | ¢
[6 empty] | Guest Room | l |  | l |  |  | ¢
[6 empty] | Wellness Center | l |  | l |  |  | ¢
[5 empty] | Course | Golf private coaching | l |  | l | 
[6 empty] | Tennis court coaching | l |  | l | 
[6 empty] | Tennis course | l | ¤ | l | ¤
[6 empty] | Golf course | l | ¤ | l | ¤
[6 empty] | Events | l | ¤ | l | ¤ |  |  | 
[7 empty] | l | Book and Access
[7 empty] |  | Book and Access if granted
[7 empty] |  | Access Only

## Status
Enrollment Status
Status | Description
Open | New Lead without member applicant
New | New application with compulsory field missing or no signature
Active(No Card) | Membership is active, but member card is not yet printed and issued
Complete | Membership is active if card is printed and payment is settled
Payment Fail | Payment has problem, and membership officer may deactivate the membership
Reject | Membership officer reject this application
Cancel | Enrollment cancelation by member
Member Status | including member and day pass guest
Status | Description
Active | Active member
Expired | Membership package expired and need renewal
Inactive | Membership is suspended/cancelled/rejected by whatever reason
Service Plan Status
Status | Description
Active | The service plan is activated
Inactive | The service plan is deactivated
Day Pass Purchase Order Status | using table <customer_order_permit_card>
Status | Description | Color
Open | The purchase order of day pass is saved, but not yet paid | Blue
Completed | The purchase order of day pass is completed after payment is settled | Green
Cancelled | The day pss is canclled for whatever reason | Red
Day Pass Card Status | using table <customer_order_permit_card>
Status | Description | Color
Issued | The day pass card is issued to guest
On Hold | The day pass card is held by HKGTA
Disposal
Staff Status
Status | Description | Color
Active | Active staff
Inactive | Staff is supsended by whatever reason
Quit | Ex-serving staff
Temp Pass Contractor Status
Status | Description
Active | Active temp pass card
Inactive | Temp pass is suspended/cancelled by whatever reason
Expired | Temp pass is expired which excess expiry date
Service Plan Status
Status | Description
Active | The service plan is activated
Inactive | The service plan is deactivated
Academy Card Status
Status | Description | Color
Active | Active academy card which is issued to member | Green
On Hand | The card is hold by HKGTA | Red
Cancelled | The card is cancelled by whatever reason | Orange
Disposal | The card is missing or damage | Grey

## Backlog
ID | User | Story name | SP | BV | Pri | Ref. ID | State | L.Update
1 | Mbe.off | Membership management - enrollment management | 34 | 55 | 1.6176 | FDSC-17 | Active
1.01 |  | View all primary member enrollment records
1.02 |  | set Academy ID manually for lucky number 7 digits, 8000000 - 9999999
1.03 |  | read salesman comment which is from sales kit
1.04 |  | send comments to salesman
1.05 |  | Show pending records with reasons(payment/missing info), salesman name and accumulated dates
1.06 |  | email order receipt payment again if necessary
1.07 |  | activate records by updating the status to "ready to print"
1.08 |  | send notification to sales kit rejection email to member when membership is rejected
1.09 |  | re-assign the enrollment process handling rights to another sales
1.1 |  | handle cancellation and refund for membership enrollment by creating refund records
1.11 |  | reject membership applications and handle refund if necessary by creating refund records
1.12 |  | View all rejected membership or dependent member application
1.13 |  | Reactivating rejected membership applications
1.14 |  | Allow to change enrollment status of member (New -> Approved -> Active(No Card) -> Complete -> Inactive)
1.15 |  | Allow to email and print the enrolment form (PDF)
2 | Mbe.off/Acc | Membership management - manage membership due | 55 | 55 | 1 | BO-18 | Active
2.01 |  | View all membership enrollments with status "payment pending" "Active (No Card)" sort by due date
2.02 |  | Sort enrollments by zero balance due(ready), enrollment date, client name
2.03 |  | add, view and edit payment details for each enrollments
2.04 |  | Automatic feed-in payment details from online credit card payment
2.05 |  | Automatic feed-in payment details from credit card reading machine
2.06 |  | Automatic feed-in payment details from sales kit
2.07 |  | Manually create cash payment details
2.08 |  | Manually create transfer, deposit or cheques payment details
2.09 |  | allow images (scanned image or photo) be attached in payment details
2.1 |  | read salesman remarks
2.11 |  | send comments to salesman
2.12 |  | send notification to salesman by sales kit when payment detail(s) is/are approved/rejected
2.13 |  | Approve or reject payment details by accountant / Mbe.off
2.14 |  | Approve enrollment if all payment details are approved
2.15 |  | update and display new balance due once a payment detail is approved
2.16 |  | generate monthly sales report of membership enrollment
2.17 |  | allow to set "payment fail" for enrollment status if payment has problem
2.18 |  | allow setting of format of invoice and receipt
3 | Mbe.off | Manage membership service plan (scheme) | 34 | 89 | 2.6176 | BO-03 | Active
3.01 |  | view all created membership scheme
3.02 |  | create & edit scheme with name, contract length, age limit, plan available date, and price
3.03 |  | allow to delete & edit a scheme if NO active member is using this scheme
3.04 |  | set rights on creating dependent members/purchasing day pass for scheme |  |  |  | Rev 1, 1.1.2
3.05 |  | set booking and access rights to functions and facilities for scheme |  |  |  | Rev 1, 1.1.2
3.06 |  | set day pass purchasing quota for scheme |  |  |  | Rev 1, 1.1.2
3.07 |  | allow to suspend/reactivate activate / deactivate a scheme so as to avoid new application
3.08 |  | Allow to search by service plan name
4 | Fd.Stf/Mbe.off | Membership management - member profiles Member Overview | 21 | 34 | 1.619 | BO-04 | Active
4.01 |  | search and edit member profile
4.02 |  | allow to set customized greeting for front-desk/telephone-desk
4.03 |  | for membership officer, provide filter advance search to find list of expiring member (30-90days)/deactivated member/by service plan) etc.
4.04 |  | for membership officer, allow to manually deactivate/activate member's membership
4.05 |  | delete no dependency member profile, i.e. newly created
4.06 |  | for membership officer, display list of profiles sort by expiration date, join date, type, status |  |  |  | FDSC-03, BO-08 | Active
4.07 |  | display all upcoming bookings for a member
4.08 |  | display personal info, account info, booking history, training history and cash value for a member
4.09 |  | display cash value balance, cash value factors and spending/top-up history for a member
4.1 |  | allow to top-up cash value at front desk by cash
4.11 |  | allow to top-up cash value at front desk by credit card
4.12 |  | Able to view list of dependent member to primary member
4.13 |  | Able to view which primary member dependent member belongs to
4.14 |  | Able to view service subscribe history of service plan
4.15 |  | Able to raise cash value refund request by member's request
5 | Tel.Stf/Fd.Stf | Membership recognition by Caller ID | 55 | 21 | 0.38182 | TD-01, FDSC-01 | Active
5.01 |  | Integration with Avaya phone system
5.02 |  | Integration with PMS and CRM so as to handle extension number from guest room
5.03 |  | Read Caller ID from phone system
5.04 |  | Display callers history with member's name
5.05 |  | display member general information, customized greeting, all bookings and membership status
6 | HKGTA | Membership recognition by Manual Search | 8 | 55 | 6.875 | TD-01, FDSC-01,FDB2-01 | Active
6.01 |  | provide quick search by academy ID or phone number or HKID or passport no (exact match)
6.02 |  | provide detailed search in membership overview
6.03 |  | display member general information, customized greeting, all bookings and membership status
7 | HKGTA | Membership recognition by Member Card | 8 | 55 | 6.875 | TD-02, FDSC-02,FDB2-01 | Active
7.01 |  | Read QR code on member card for recognition
7.02 |  | display member general information, customized greeting, all bookings and membership status
8 | Fd.Stf | S-beacon member recognition | 34 | 34 | 1 | FDSC-23, AWS-09 | Active
8.01 |  | Records nearby member by ibeacon
8.02 |  | Show nearby member names and photos on screen
8.03 |  | Show details info of member to show by selecting the "found" members
8.04 |  | Show customized greeting setting
8.05 |  | allow to set used beacon
9 | Meb.off/Fd.Stf | Manage and issue primary or dependent membership cards | 55 | 89 | 1.6182 | FDSC-10 | Active
9.01 |  | handle and send dependent member creation request to management
9.02 |  | create dependent member by allowing customer to fill-in form and sign consent on form kit at front desk
9.03 |  | View all members with status equal to "ready to print"
9.04 |  | allow to print member ID, member name, expiry date any new card printed with QR code
9.05 |  | Link printed card by card's QR code for each dependent member
9.06 |  | set "ready to collect" to "activated" when member is to collect the card by reading the QR code
9.07 |  | allow also the creation of primary and dependent member on PC application
9.08 |  | allow the card replacement and deactivate the old one in system
9.09 |  | for primary member, print card with status "Active (No Card)" and then link the card with QR code(Status change to "Complete") Able to change card status (Issued/Onhand/Disposal)
10 | Mbe.off | Card management - display of membership card issue history | 8 | 8 | 1 | FDSC-12 | Active
10.01 |  | view all member cards created by time i.e. today, weeks, months or specified period Provide advance search for find list of member card created by time i.e. today, weeks, months or specified period
10.02 |  | view all expired member cards, i.e. expired for weeks, months, expiring in weeks/45 days/month(s) provide advance search for find list of disposal member card
11 | Fd.Stf | Issue online purchased day pass | 34 | 89 | 2.6176 | FDSC-13,16 | Active
11.01 |  | Read and validate the day pass QR code shown on customer apps (by Scan button)
11.02 |  | Read primary member card QR code to show all purchased day pass
11.03 |  | Show primary member/dependent member i.e. the purchaser info
11.04 |  | Show the day pass user info
11.05 |  | edit/update day pass user info if there is any missing field, allow user to use Form KIT to input field
11.06 |  | Show all purchased day pass by member
11.07 |  | Link a card by the card's QR code for "issuing Ready to Active" a day pass only when activate date is today
11.08 |  | allow the day pass user to enter user information and sign consent with tablet (Form Kit)
11.09 |  | set day pass valid period based on the purchased number of consecutive days
11.1 |  | System auto change status of day pass to 'Ready to Active' once today is activate date
12 | Fd.Stf | Issue day pass at front desk by direct purchase | 34 | 55 | 1.6176 | FDSC-13,16 | Active
12.01 |  | Validate member day pass purchase rights with member's card, i.e. granted? Weekday (weekday member) cannot buy weekend (Full day member)
12.02 |  | check day pass quota and member's quota, avoid over purchase
12.03 |  | allow to create multiple day pass under one member
12.04 |  | allow to select multiple day pass under one member for payment settlement
12.05 |  | link QR code on a card for "issuing" a day pass
12.06 |  | allow staff to enter day pass user(s) information before purchasing and user(s) to sign consent with tablet (Form Kit)
12.07 |  | allow also the day pass user(s) to enter user(s) information and sign consent with Form KIT
12.08 |  | store, print/email order receipt after day pass settlement
12.09 |  | allow to choose adult and child version of one day pass with price different |  |  |  | Rev.#1 CRM1.1.2
12.1 |  | set day pass valid period based on the purchased number of consecutive days
13 | Sales | Manage sales kit for customer - presentation | 13 | 34 | 2.6154 | BO-04, 05 , 06 | Active
13.01 |  | Create presentation from different image folders on the application server
13.02 |  | Allow to send presentation to member customer by email in PDF format with customized email body based on the email template from server
13.03 |  | View presentation list filtered by the sales or all sales
13.04 |  | Allow to reorder the presentation slides and save customized presentations per account
13.05 |  | Allow to delete the presentation
13.06 |  | Sort presentation list by File Name, Last Update and Created By
13.07 |  | Search presentation by presentation name
13.08 |  | View full screen presentation
13.09 |  | Allow to copy other sales presentation (Save as)
13.1 |  | Allow to play videos in the presentation
13.11 |  | Able to view presentation (only image) in offline mode, including image and videos
14 | Sales | Sales KIT Individual Primary membership enrollment - registration anywhere | 55 | 144 | 2.6182 | BO-07 | Active
14.01 |  | allow primary member to fill-in personal information for registration on sales kit
14.02 |  | allow primary member to sign on tablet for registration
14.03 |  | take primary member photo for registration
14.04 |  | allow primary member to provide photo for registration
14.05 |  | allow to leave remarks for each enrollment
14.06 |  | allow to edit/update the enrollment
14.07 |  | allow to check and use lucky unique ID (7 digits, 8000000 - 9999999)
14.08 |  | notification of new remarks from membership officer and allow to read
14.09 |  | only allow deleting enrollment records without payment details, i.e. missing info/payment pending
14.1 |  | Select notification priority - Apps, Email, SMS, Phone Call
14.11 |  | allow preview of inputted information before submitting primary member info
14.12 |  | create member by linking a card with its QR code and issue card (printing of ID & payment can be delayed)
14.13 |  | allow to manually active the membership of an enrollment record when all compulsory registration input is done, status change to "Active(No Card)"
14.14 |  | automatically set status to "Payment pending" for enrollment with outstanding payment
14.15 |  | Allow to send email activation letter (attach with payment receipt if the payment is done) with customized email body based on the email template from server
14.16 |  | remove activated member from membership enrollment list once all payments are approved and card is issued (move to enrollment history) enrollment status is complete update enrollment statue of member to be 'Complete' once all payments are approved and card is issued
14.17 |  | provide views to see all enrollment records with status and all activation history of member, filtered by a targeted sales or all sales, enrolling / completed / Inactive
14.18 |  | Allow to sort the enrollment records by Member Name, Enroll Status, Enrollment Date and Service Plan
14.19 |  | Allow to search the enrollment records by First Name, Last Name and Company Name
14.2 |  | Automatically create transaction record once enrollment is created member is activated
14.21 |  | Allow to upgrade to be primary member when system identify member type of customer is dependent member
14.22 |  | Allow to send the enrolment form(PDF) without the e-signature to customer for further consideration
14.23 |  | Disallow activating a membership
14.24 |  | Allow to reserve the academy ID for future enrollment
15 | Mbe.off/Sales | Sales KIT Individual Primary membership enrollment/renewal - payment settlement anywhere | 55 | 89 | 1.6182 | BO-07 | Active
15.01 |  | view my membership enrollment list with status, payment due |  |  |  | BO-08
15.02 |  | handle online credit card payment
15.03 |  | take photos on cheques and transcripts for bank transfer, cheques bank-in and deposit
15.04 |  | allow sales to leave remarks for each member
15.05 |  | allow sales to read comments for each enrollment from membership officers
15.06 |  | allow sales to check lucky academy ID availability and set unique lucky ID (7 digits, 8000000 - 9999999)
15.07 |  | submit payment & management approval request
15.08 |  | create list of payment details, i.e. auto feed-in online payment info, manual attach photo of cheques & transcript
15.09 |  | email payment receipt to customer for each payment
15.1 |  | view all payment details for each enrollment
15.11 |  | prepare pro-forma invoice for member who want to pay by his/her company account, allow to fill-in billing info and send invoice
15.12 |  | set enrollment status to "Ready to Active" once all payments are done
15.13 |  | allow adding new payment details for suspended enrollment and reactivate account once payment is settled again
15.14 |  | display 20 latest enrollment activities on sales kit
15.15 |  | View transaction list filtering by Pending Payment / Completed Payment, Enrollment / Renewal
15.16 |  | Search transaction list by First Name, Last Name and Company Name
15.17 |  | Sort transaction list by Member Name, create date, type, Amount and Balance Due
16 | Fd.Stf | Form filling and consent signature on Form KIT | 34 | 89 | 2.6176 |  | Active
16.01 |  | allow staff to chose suitable forms, e.g. choose dependent member form, and input primary member ID
16.02 |  | allow customer to sign on tablet for making a consent
16.03 |  | allow customer to fill-in form on tablet
16.04 |  | allow taking photo/getting photo of/from customer for the form on tablet
17 | Mbe.off | Manage the day pass | 34 | 55 | 1.6176 | FDSC-14,15 | Active
17.01 |  | set day pass global quota |  |  |  | Rev.1, 1.1.2
17.02 |  | set day pass price profile on calendar so that adult/children and its high/low price can be set daily |  |  |  | Rev.1, 1.1.2
17.03 |  | set weekday price as low and weekend price as higher by default
17.04 |  | deactivate/reactivate an issued day pass
17.05 |  | show issued day pass history for 30 days, 90 days(default), 12 months or specified period by advance search |  |  |  | Rev.1, 1.1.2
17.06 |  | show summary for day pass issued, i.e. day pass sold, revenue in month |  |  |  | Rev.1, 1.1.2
17.07 |  | create day pass for customer by day pass profile settle payment of multiple day pass profile and create payment record
17.08 |  | create day pass profile with name, referral type, price, access rights and price profile on calendar
17.09 |  | stores day pass history for 7 years only |  |  |  | Rev.1, 1.1.2
18 | Mbe | online purchase of Day pass on apps (Web Portal and Member App) | 55 | 89 | 1.6182 | AWM-43 | Active
18.01 |  | check member's right on purchasing day pass, i.e. Granted? Weekday member cannot buy weekend day pass
18.02 |  | show day pass purchase quota for that member
18.03 |  | select day pass effective date(s) and quantity of day pass
18.04 |  | enter friend's basic information for each day pass before purchasing, i.e. name and phone number
18.05 |  | online payment gateway connection and settle payment
18.06 |  | email order receipt to member after successful purchase of Day pass
18.07 |  | display purchased ready-to-use day pass
18.08 |  | forward the day pass (a QR code) to friend by WeChat, WhatsApp, Email with a link to show QR code
18.09 |  | allow saving QR code in phone for other forwarding process
18.1 |  | use cash value to settle payment settle payment of multiple day pass profile and create payment record
18.11 |  | for primary member, allow to use cash value with credit limit for settlement
18.12 |  | for dependent member, allow to use cash value with credit limit of their primary member for settlement
18.13 |  | allow to buy on credit if primary member has direct debit agreement
18.14 |  | allow to choose adult and child version of one day pass with price different |  |  |  | CRM1.1.2
19 | Mbe | Member APP - Manage dependent members (Web Portal and Member App) | 13 | 34 | 2.6154 | Rev 1, 1.1.3 | Active
19.01 |  | display list of dependent members
19.02 |  | grant booking rights of 1)facilities right 2)private coaching & course 3)Events
19.03 |  | grant day pass purchasing rights
19.04 |  | set per transaction spending limit
19.05 |  | View profile of depend member
20 | Mbe | Manage my account (Web Portal and Member App) | 13 | 21 | 1.6154 |  | Active
20.01 |  | Show my membership details
20.02 |  | Show my Cash Value
20.03 |  | Top-up cash value by online credit payment
20.04 |  | View all my transaction history including all payment done online/offline, for primary member, transaction of dependent member is included
20.05 |  | allow edit and update of my membership details (except compulsory field)
20.06 |  | Show my Virtual Account Number
20.07 |  | Allow to set security question which used to reset password in Forget Password page
21 | Mbe.off | Manage Temp Card | 21 | 55 | 2.619 | Rev 1 | Active
21.01 |  | View all activated temporary cards and sort by date by advance search
21.02 |  | View all deactivated/expired temporary card by advance search
21.03 |  | Activate or Deactivate an issued temporary card
21.04 |  | create or delete temp card profile, i.e. card name, valid period, booking and access rights to facilities
22 | Fd.Stf | Issue temp pass at Front Desk | 21 | 55 | 2.619 | Rev 1 | Active
22.01 |  | allow to create for multiple new temp pass with selection of temp card profile allow to issue new temp pass with one selected temp pass profile
22.02 |  | input temp user(s) info for new temp pass by Form KIT or front desk themselves
22.03 |  | Register the QR code on a card for "issuing" the temp pass
22.04 |  | set temp pass validation period for each new card
23 | Mbe.off | Sales kit(tablet apps) membership renewal - payment settlement | 55 | 89 | 1.6182 |  | Active
23.01 |  | Recognize member on tablet
23.02 |  | View list of expiring members and filter them by Expire In 30/60/90 days
23.03 |  | handle online credit card payment
23.04 |  | take photos on cheques and transcripts for bank transfer, cheques bank-in and deposit
23.05 |  | create list of payment details, attach photo of cheques/transcript
23.06 |  | Send renewal email with customized email body based on the template file to customer after receiving all payment details, record this action
23.07 |  | view all payment details for each renewal record
23.08 |  | preparation of invoice, allow to fill-in billing info and send invoice if necessary, record this action
23.09 |  | extend the period based with renewal plan details if all payment is done
23.1 |  | Allow to set new plan for the member and renew the member service plan
23.11 |  | Automatically create transaction record once renewal is created
23.12 |  | View member info
24 | Mbe.off | Membership Management - membership renewal | 55 | 89 | 1.6182 |  | Active
24.01 |  | view all expiring members in member overview with advanced search
24.02 |  | automatically set all 45 days expiring member status from "active" to "expiring"
24.03 |  | automatically email "extension of membership letter" to expiring members with contact info of membership officer (with default 30 days)
24.04 |  | create and edit extension of membership letter template in template management
24.05 |  | system permanently store expired member details with a status including cash value balance for reuse
25 | Mbe.off | Membership Management - corporate management | 55 | 89 | 1.6182 | Rev 1 | Active
25.01 |  | allow to create/edit/delete corporate account
25.02 |  | allow to create/edit/delete primary member under corporate account
25.03 |  | allow to create/edit/delete dependent member(s) under corporate primary member
25.04 |  | allow to set credit limit for each corporate primary member based on total credit limit of corporate account
25.05 |  | summarize the spending by credit limit from all members and bill the corporate in a default period
25.06 |  | allow to set credit limit for each corporate account
25.07 |  | allow to enter contract refer no. on corporate account
25.08 |  | allow to set new service plan of corporate
25.09 |  | allow to deactivate the corporate account. It make all related corporate member to be inactive at the same time
26 | Mbe.off | Membership Management - virtual account bank integration(individual & corporate) | 89 | 89 | 1 | Rev 1 | Active
26.01 |  | create virtual account for new member after activation by adding input in CSV file with defined format
26.02 |  | send the virtual account creation request in batch by the CSV file to the HKGTA sftp server (HKGTA server forwards the file to bank)
26.03 |  | read virtual account creation result from HKGTA sftp server, and then update the system with the result
26.04 |  | read virtual account balance and update the system
26.05 |  | allow to automatically transfer money from virtual account to member's cash value
27 | Mbe.off | Membership Management - direct debit bank integration(individual & corporate) | 89 | 89 | 1 | Rev 1 | Active
27.01 |  | allow to manually input direct debit details for a primary member
27.02 |  | allow to set credit limit based on the direct debit details
27.03 |  | integrate bank and handle the direct debit instruction for payment settlement
27.04 |  | allow credit limit be used among primary member and all related dependent members
27.05 |  | allow buy on credit through credit limit once cash value need to overdrawn, if direct debit account is ready
27.06 |  | reset cash value to zero if the direct debit account successfully pay the overdraft off
28 | Mbe.off | Membership Management - notification center | 89 | 89 | 1 | Rev 1 | Active
28.01 |  | allow to send Email to customer for notice purpose
28.02 |  | allow to send SMS to customer for notice purpose
29 | Mbe.off | Membership Management - KPI | 89 | 89 | 1 | Rev 1 | Active
30 | Sales | Manage sales kit for customer - general features | 34 | 89 | 2.6176 |  | Active
30.01 |  | allow login and logout
30.02 |  | allow to show all enrollment status among sales, e.g. new enrollment, completed enrollment etc.
30.03 |  | show notifications alert at front page, e.g. payment approved, new remarks from management, etc.
30.04 |  | allow to search all enrollment records (include other salesman) by name
30.05 |  | allow to enter potential customer details with photo for sales activities
30.06 |  | show list of potential customers, my customers should show first on the list
30.07 |  | allow to view/search a potential customer details (first name, last time, company name)
30.08 |  | display 20 latest enrollment activities on sales kit
30.09 |  | Show number of prospects, number of presentations, number of active members, number of members expires in 30 days and number of payments pending in home page
31 | Mbe.off | Manage sales kit for customer - Leads | 34 | 89 | 2.6176 |  | Active
31.01 |  | View lead list by Lead Name, Sales Person, status and Creation Date and filter by my leads and all leads
31.02 |  | Search leads by First Name, Last Name and Company Name
31.03 |  | Sort lead list by Lead Name, Sales Person, status and Creation Date
31.04 |  | Create, update and delete lead
31.05 |  | Show indicator if there is unread remarks
31.06 |  | Read and write remarks
31.07 |  | Allow to send the presentation in a pdf file format by email from server
31.08 |  | Allow the lead to enroll a membership
31.09 |  | View leads detail
31.1 |  | Can edit the note in a new section
31.11 |  | Allow to classify the lead's role
26 | Mbe.off | Membership Management - membership rejection, cancellation and refund | 89 | 89 | 1 | Rev 1 | Active
26.01 |  | allow the customer to use Form Kit to make cancellation request
26.02 |  | allow to manually create cancellation requests at back office(for requests from paper form or rejection done by officer)
26.03 |  | allow to view all cancellation requests
26.04 |  | allow to approve cancellation requests by creating refund records for accountant
26.05 |  | allow to create remarks for each refund record
26.06 |  | allow to set refund amount in refund records
26.07 |  | show all transaction history of member account for each cancellation requests
32 | Mkt.off | Manage sales kit presentation's template files (Web portal) | 13 | 34 | 2.6154
32.01 |  | allow to create folder for storing images
32.02 |  | Upload images to a folder and generate thumbnail for the image
32.03 |  | Delete image in the folder, so that the related image in the presentation will no longer be displayed to the customer. (Mark delete only)
32.04 |  | allow to import videos in the template folder, and generate thumbnail for the video
32.05 |  | allow to restore videos or image in the trash
32.06 |  | Allow to import PDF file and convert PDF file into image file (one page = one image)
33 | Mbe.off | Sales Kits Backend and Frontend Integration
33.01 |  | Sales kit Support
33.02 |  | Sales kit bug fix due to database table changes
34 | Mbe | General feature (Member app)
34.01 |  | Read notification messages with unread indicator
34.02 |  | Allow to auto login
34.03 |  | View and refresh current weather, such as temperature and weather conditions
34.04 |  | View advertisement banners and its content
34.05 |  | Generate and show my QR Code
34.06 |  | Support multiple language (English / Traditional Chinese)
35 | Sales.off | Advertisement Banner Management
35.01 |  | Manage advertisement items
36 | RR | Member recognition apps on Tablet for restaurant / retail
36.01 |  | recognize a member by ibeacon
36.02 |  | display member general information, customized greeting, all bookings and membership status
36.03 |  | integrate with the POS terminal and recognize member when POS terminal read member card by QR code
37 | Fd.Stf/Mbe.off | Member recognition history
37.01 |  | Able to show search history with 20 record
37.02 |  | Able to view detail of member info
38 | Sales.off | Sales KIT Individual Dependent member creation of primary member
38.01 |  | Allow to create dependent member once primary member start enrollment process
38.02 |  | Allow to fill-in info of dependent member with required field (like HKID)
39 | Rest.off | Resturant CRM App - member recognization and profile
39.01 |  | Can recognize members by iBeacon technology
39.02 |  | Can recognize members by scanning the member's QR Code in POS
39.03 |  | Can view the member profile
40 | Acc | Refund Management - Cash Value
40.01 |  | View list of refund request
40.02 |  | View detail of refund request (member info, request info)
40.03 |  | Able to reject the refund request
40.04 |  | Allow to process refund (including type in reference no and confirm refund amount)
40.05 |  | The refund value is credited from member's cash value account automatically after accountant approve the amount
40.06 |  | System send the notification email to member, success or rejected refund
41 | Mkt.off | Template Management
41.01 |  | allow to view all kind of template by category
41.02 |  | Update and save email info including subject and email content
41.03 |  | Allow to use HTML format in email content
42 | Mbe.off | iBeacon Management
42.01 |  | View list of beacon
42.02 |  | Edit ibeacon info (beacon id, localion type, bacon name)
42.03 |  | Check availablty of beacon id. One ibeacon id only can be used in one local type
42.04 |  | Allow to Edit beacon major #. Default is 1
43 | Mbe | General Feature - Member Web portal
43.01 |  | Allow to Login / Log out
43.02 |  | Allow to reset password by answering security Question
43.03 |  | Support multiple language (English / Traditional Chinese)
44 | Mbe.off | Membership Management - Monthly statement management
44.01 |  | view all members' statements on webpage by month, show current cash value balance of members based on selected month
44.02 |  | provide filtered view for members' statements, e.g. list all outstanding statement with negative balance last month
44.03 |  | automatically generates monthly "credit balance" statement for all members, i.e. cash value balance, top-up history, VA history, credit status
44.04 |  | automatically send monthly statement to all members by default email in PDF format
44.05 |  | allow to download the PDF formatted monthly statement of a member
44.06 |  | allow to set the default email address for sending statement
44.07 |  | allow to resend monthly statement instantly upon request

## Dependency
ID | Task Name | Predecessors
10 | Start
100 | Membership management - enrollment management | 1400
200 | Membership management - manage membership due | 1400
300 | Manage membership service plan (scheme) | 10
400 | Membership management - member profiles | 1400
500 | Membership recognition by Caller ID | 10
600 | Membership recognition by Manual Search | 10
700 | Membership recognition by Member Card | 10
800 | S-beacon member recognition | 1400
900 | manage and issue primary or dependent membership cards | 1400
1000 | Membership management - display of membership card issue history | 900
1100 | Issue online purchased day pass | 1700
1200 | Issue day pass at front desk by direct purchase | 1700
1300 | Manage sales kit for customer - presentation | 10
1400 | Sales kit(tablet apps) membership enrollment - registration anywhere | 300
1500 | Sales kit(tablet apps) membership enrollment - payment settlement anywhere | 1400
1600 | Form filling and consent signature on Tablet (independent apps on tablet) | 10
1700 | Manage the day pass | 300
1800 | online purchase of Day pass on apps | 1700
1900 | Manage dependent members on apps | 1400
2000 | Manage my account on apps | 1400
2100 | Manage Temp Card | 10
2200 | Issue temp pass at Front Desk | 2100
2300 | Sales kit(tablet apps) membership renewal - payment settlement at HKGTA | 1400
2400 | Membership Management - membership renewal | 1400
2500 | Membership Management - corporate management | 10
2600 | Membership Management - virtual account bank integration(individual & corporate) | 1400
2700 | Membership Management - direct debit bank integration(individual & corporate) | 1400
2800 | Membership Management - notification center | 1400
2900 | Membership Management - KPI | 1400
3000 | Manage sales kit for customer - general features | 10
20 | Finish

## User Story Supplement
ID | User | Story name | Story Description
14 | Sales | Sales kit(tablet apps) Individual Primary membership enrollment - registration anywhere | The flow of enrollment by Sale KIT: 1. Member fill-in the application, status changes to "New" 2. Salesman can activate the member on Sales KIT once form filling and signature are done, payment can be settled later 3. Salesman send the activation email to member's register email 4. Status change to Active(No Card), Payment can be settled AFTER membership activaton. 5. Card is printed and linked into the system with the QR code at PC application (at HKGTA) 6. Status changes to "Complete" on Sales Kit once Card is printed and payment are settled. Exceptional case 1. Member enrollment can be rejected by membership officer. The enrollment status is manually changed to "reject" by officer at PC application(back office) 2. Member enrollment can be cancelled by member. The enrollment status is changed to "cancel" by officer at PC application(back office) 3. "payment fail" is an enrollment status set by membership officer if there are payment problems. Membership officer may deactivate the membership status.
14.16 | Sales | uppdate enrollment statue of member to be 'Complete' once all payments are approved and card is issued | The enrollment status of member can be changed to 'Complete' when all payment is approved by account/membership officer and member card is issued
30.09 | Sales | Show number of prospects, number of presentations, number of active members, number of members expires in 30 days and number of payments pending in home page | number of prospect --> enrollment status is 'Open' Number of active member --> enrollment status is 'Complete' & 'Active (No card)'
2.12 | Mbe.off/Acc | send notification to salesman by sales kit when payment detail(s) is/are approved/rejected | in this story, accountant can review the payment and verify the validation of payment detail. He/she can change status of each payment detail. Herewith the rule to change status 1. after salesman enter payment detail, the status is NULL as default 2. Accountant can click Edit to change status to Success / Failure of each payment detail 3. No more action can be done, if accountant change status to be 'Failure' 4. Accountant can 'Void' the payment detail after accountant change status to be 'Success'
16.01 | Meb | allow staff to chose suitable forms, e.g. choose dependent member form, and input primary member ID | In form Kit, it shall allow to create dependent member for primary member 1. enter memner id 2. If dependent member, it shall allow to update profile of dependent member 3. If primary member, it shall show list of dependent member first and allow to create dependent member